## Template
Project:
Project Sponsor:
Project Manager:
Phase | Deliverable | Work | Work Detailed | Completion Criteria | Planned Effort
Initiating
Organize Initiating Phase
Gather Key Initiating Resources
High-level User Requirements
Identify and Interview Key Stakeholders
Determine Stakeholder level of engagement and success criteria
|  | Gathering High-level Requirements Appropriate for the Business Decision |  | Must have requirements for final deliverable
Project Charter
|  | Define Project Goals |  | Use SMART
|  | Determine Final Deliverables |  | Agreed to by Sponsor and key stakeholder
|  | Review Industry Standards, Best Practices and Lessons Learned |  | Talk to PMs of similar in-house projects and search web for best practices
Gather Assumptions and Constraints
|  | Determine High-level Time Line |  | Meets business need
Determine Project Priority in Work Area
Review Existing Workload and Resource Availability
Define Key Resources Requirements
|  | Determine High-level Cost / Benefit Analysis |  | Use department template
Document and Present Project Charter
Initiating Phase Total
Planning
Organize Planning Phase
Gather Key Planning Resources
Hold Planning Core Team Kick-off
Project Plan
|  | Confirm Goal |  | Still SMART
Define Scope
Clarify Final Deliverables
|  |  | Identify Interim Deliverables | Defined and added to this spreadsheet
|  |  | Define Acceptance Criteria for each Deliverable | Defined by 'owner' of each Deliverable
Confirm Impacted Areas
Document Exclusions
|  | Identify, Assess and Develop Risk Management Strategy |  | Use Risk Register template
Determine Procurement Requirements
Create WBS
|  |  | Determine Work to Complete Project Deliverables | Defined and added to this spreadsheet
|  |  | Assign Resources and Estimate Effort to Work | Defined and added to this spreadsheet
|  | Define Project Roles & Responsibilities |  | Use R&R Matrix
|  | Create Schedule |  | Updated in this spreadsheet, confirm availability of key Resources
|  | Create Network Diagram to Determine Critical Path and Project Duration |  | Project duration matches or is less than project end date
|  | Create and Confirm Project Budget From Project Charter High-level Estimate |  | Use template
|  | Document and Present Project Plan |  | Summary Plan in ppt created for Sponsor and Key Stakeholder presentation
|  | Create Communication Plan |  | Includes all TM and Stakeholders
|  | Document Roles & Responsibilities on How Issues Will be Tracked and Communication |  | Make updates to R&R Matrix
|  | Create Issue Log |  | On shared drive
|  | Document Authorities Around Identifying, Rejecting and Accepting Changes |  | Make updates to R&R Matrix
|  | Create Change Log |  | On shared drive
Planning Phase Total
Create Stakeholder Management Plan
Execution & Control
|  | Organize Execution & Control Phase |  | Plan Kick-off
|  | Gather Execution & Control Resources |  | Secure Resources
Establish Baselines For Tracking Against Time, Cost and Quality
|  | Hold Kick-off Meeting |  | With Sponsor communicating business need
Project Plan - Updates (these are on-going based on the project plan and can be included in specific deliverable WBS works)
Manage Risks
Manage Issues
Manage Scope Changes
Engage Stakeholders
Manage Procurement
Execute Communicaiton Plan
|  | Track Acceptance Criteria for each Deliverable |  | Acceptance Met for each Deliverable
Develop Project Team
|  |  | Provide Performance Feedback | One-on-Ones each week
|  |  | Provide Rewards and Recognition | Pizza at Milestones
|  |  | Hold Team Meetings | Per Comm. Plan
On-board new team members
Status Reports
|  | Track and Record Actuals for time and budget |  | updates to spreadsheet
|  | Update Schedule |  | updates to spreadsheet
Review Issue and Change Log
Create Status Reports Per Communication Plan
Hold Status Meetings Per Communication Plan
* Project Deliverable 1
Work 1
Work 2
Work 3
Work 4
Work 5
Work 6
Work 7
Work 8
Work 9
* Project Deliverable 2
Add work for Deliverable 2 Here
* Project Deliverable 3
Add work for Deliverable 3 Here
* Project Deliverable N
Add work for Deliverable N Here
Execution & Control Phase Total
Closing
Close Out Project Costing
|  | Close Out Procurement |  | Contacts closed
|  | Provide Team Members Performance Feedback |  | Formal written feedback to each Resource
Post Project Review
|  | Gather Actuals |  | Compare to Planned
Time
Cost
Benefits Received
Gather Lessons Learned From All Project Participants
|  | Document and Present Post Project Review to Entire Project Team |  | Pizza
Closing Phase Total
* Project Deliverables Can Included But Are Not Limited To:
Products
Designs / Prototypes
Materials List
Request For Proposal
Distribution Plan
Implementation Plan
Manufacturing Plan
Marketing Plan
Pricing Strategy
Requirements Documentation
Service Level Agreements
Training
Documentation
Quality Plan / Test Plan